## Introduction
Date:
Project: | NJSBDC.COM Web Site Home Page Refresh
Planning: | This is a worksheet to develop the plan.
The project plan method is iterative.
Author(s):
Version: | 1
Tab 2 | Planning & Timing
Tab 3 | Plan Outline
Tab 4 | Setting Objectives
Tab 5 | Details - Review

## Plan&Time
Deliverables & Timeline
Objectives | Visitors | UX | Features | Operations | Prototype: Dev Site (Plan A) | Prototype: Dev Site (Plan B) | Price and time estimates for refresh | Management Approvals | Execute and launch changes | Monitor and tweak (adjustments based on matrices)
Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X
Document the home page planning process and the set the objectives for project. | Document the audience segments, profile users, the buying process and the assets that will be used. | Create a conceptual path for visitors, an outline for the brand vision and the user experience. | Document the features and the corresponding priority. | Document the key business processes, critical success factors and metrics to gauge performance. | Build out a visual protoype on a free service like Weebly to demonstrate the lok and feel of the proposed new Home Page. | Based on paraeters of web site. Based on cost to update. There is always the Plan B.
Deliverables | Deliverables | Deliverables | Deliverables | Deliverables | Deliverables | Deliverables | Deliverables | Deliverables | Deliverables | Deliverables
Home page plan | Target audience(s) | Conceptual architecture | Feature roadmap | Enabling processes | Build out a visual protoype
Objectives | Personas | Brand vision |  | Critical success factors
| Buyer behavior model | User experience |  | Success matrices
Journey board

## Plan Outline
I. | WEBSITE UPDATING PLANNING PROCESS
| A. | BRANDING
|  | 1) | Thematic tie to SMALL BUSINESSS BIG IMPACT brochure
|  |  | a) | Evaluate the use of the theme in digital format
|  |  | b) | Analyze best layout for theme within the parameters of the existing template
|  |  | c) | Structure or resturcture existing content (images and words, sizes and power packed feeling) into digital frame.
|  | 2) | Today's analysis and 'face lift of home page" needs to relate to future web site modification (24 months-out).
| B. | HOME PAGE FACE LIFT
|  | 1) | Setting objectives, delverables and timeline
|  |  | a. | Target audience & personas (Target Market Identifiers)
|  |  |  | i. | Visitor/client behavior model
These elements include clear definitions of who the website is intended for, broken down by degrees of priority and the unique audience needs the website must address.
|  |  |  | ii. | Journey board
|  |  |  | iii. | Conceptual architecture
|  |  |  | iv. | Brand vision & user experience
[5 empty] | aa. | Relevancy creates value
Relevancy connects business goals with audience needs. Redesigning the experience to be in line with the expectations of the target audience provides relevancy.
[5 empty] | bb. | Usability creates understanding
Usability connects user goals with infomration structure, organzation and interaction.
[5 empty] | cc. | Desirability creates loyalty
Desirability helps connect brand goals with interaction, image and tone. This connection builds loyalty for the user experience.
|  |  |  | v. | Feature roadmap
Outlines the short and long-term features and content requirments for the website.
|  |  |  | vi. | Enabling process & critical succes factors
Identifies the supporting business processes required to effectively operate the website.
|  |  |  | vii. | Success metrics
Defines how success will be measured once the redesign launches.
|  |  |  | viii. | Reporting tools
|  |  | b. | Content
|  |  |  | i. | Adding a site search feature
|  |  |  | ii. | Social Media
|  |  |  | iii. | New Slider: photos and messaging
[5 empty] | aa. | Restructure messaging based on new/researched information
[5 empty] | bb. | Evaluating layout/positioning - which may be fine with improved modern layouts (and theme)
[5 empty] | cc. | Focus on packages of 3-4 slides updated quarterly (tie into major event/subject matter)
[5 empty] | dd. | Evaluate and change image and words, position of banners, order of presentation.
|  |  |  | iv. | Mobile Strategy
|  |  |  | v. | Keyword/Key Phrases / Indices
|  |  |  | vi. | PPC / Google Adwords
|  |  | c. | Layout
|  |  |  | i. | Within parameters of template, possibly change (update) the template.
|  |  | d. | Email capture (Incorporate a capture Mailing List pop-up)
|  |  |  | i. | Build a community
|  |  |  | ii. | Build sub communities
|  |  | e. | Marketing automation
|  |  |  | i. | Build a community
|  |  |  | ii. | Build sub communities
| C. | Restructure entire web site
(May 2018-24 months)

## Brand Vision
Brand Vision
Benefits | Why do people find the offering / company to be appealing?
What does the organization do - at a high level?
What does your organization understand about the problem, solution and/or user that other vendors do not?
What is the impact on the business?
Target | Who do I appeal to?
Why do business users like you?
What are they concerned about and how will you impact their business life?
Why do technical users like you?
What are they concerned about and how will you impact their business life?
Relationship | How do I interact with them?
Are you active or reactive?
Do you speak about business value?
Do you speak in jargon or plain English?
Do you sell or listen to business problems and share insights about how others have solved similiar problems for similiar companies?
Character | Inspiring - unrelenting efforts, never doubt the possibility of success, innovation and excited to accept a new challenge.
Incisive - turn insight into practical action. Translate business needs into products and solutions. Exude clarity in everything we do. Simplify the complex.
Confidence - Unrivaled experience in the indutry. Rich heritage in cnsulting and thought leadership. Not arrogant. Exude appririate level of self-confidence.
Trust - Private and confidential.
Development
How do I need to change?
Is your organzaition a leader or a follower?
Does your organization have bleeding edge (state of art/ahead of curve), deliverables?
Does your organzation see the problem the same way competitors do?
Does your organzation see the solution the same way competitors do?

## Target
Target Audience
| Description | Priority for (short term) New Home Page | Priority for (long term) New Site
Customer | This is an entrepreneur just starting out or a business owner of a matured company who have turned to the NJSBDC in the past and continue to come back for consulting services and loans. The customer may be returning to the site regularly for educational materials, an update on events or to conduct research on say a new tax law seeking information and support. Efficient and effective search, clear navigation workflow. 24/7/365 access. Secure access. Enabling a high degree of self service are key for this audience. | Primary | Primary
Prospect | This is an entrepreneur just starting out or a business owner of a matured company who should turn to the NJSBDC for consulting services and loans. This is someone who could be an absolute stranger to the NJSBDC or someone who has experienced services and is returning to the site regularly for educational materials, an update on events or to conduct research on say a new tax law seeking information and support. Efficient and effective search, clear navigation workflow. 24/7/365 access. Secure access. Enabling a high degree of self service are key for this audience. | Secondary | Primary
Partner | This audience seeks to strengthen the alignment or analyze if an alignment is good. This audience can also be program sponsors.experienced services and is returning to the site regularly for educational materials, an update on events or to conduct research on say a new tax law seeking information and support. They will return ot eh site offen and expect efficient and effective search, clear navigation workflow. 24/7/365 access. Secure access. Enabling a high degree of self service are key for this audience. | Teritiary | Secondary
Investor | This audience seek information to understand who the organization is, why it is different and how it builds value. For investors, the information needs to be easy to find, easy to access, easy to read and easy to comprehend. The goal is for investors to have a positive opinion of the organization and to be optimistic about it's future. | Teritiary | Teritiary
Influencers | The influencer audience typically works on deadlines so they need clear access to content that is in one place and can be accessed in real-time. Content is required in a format that can be repurposed to perform their promotions/publishing. The goal for influencers is for them to have a positive opinion of the organization and to be optimistic about it's future. | Secondary | Secondary
Employment | This is two fold. The existing employees want to be proud of where they work and the web site is one of the most obvious places where they can be judged by the place they work. The other is to attract new employees, consultants, advocates, volunteers, interns. | Quaternary | Secondary

## Feature Roadmap
Feature Roadmap
Meta Features | Search
Social Media
Instant Survey
Opt In Email
Contact Us
Client Management | IC Net
Lifecycle: From stranger to inquired to counseled)
Training events
Sponsor events
Collaboration (SBA, et al)
Loans issued
Driving advocacy groups
Service & Support | Success stories
Success blogs
Success hyperlinks
Success awards
Testimonials
Centers
Drive counseling opportunities
Drive loan opportunities
Drive trainees
Knowledge Base
Downloadable items
White Papers
Webinars
Case Studies
General Business Forms
Ask a Question
Interaction
Sales & Marketing | Specialty Programs
ROI Calculator
Client Journey
Moving from stranger to client (Headquarters and/or Center)
Training Events
Award Events
Sponsorships
Government Advocacy

## Process
Enabling Process & Critical Success Factors
Business Process | Process Description | Business Requirements
Ownership and Governance | Determination and definition of content. Authority to upload. Staffing structure to manage, maintain and implement future releases. | Identification within the organization chart of a "website director" (ideally one with one foot in IT and one in marketing) responsible for successful implementations of intiatives.
Content Development and Management | Copywriting, editing, designing, versioning, producing, posting and retiring of content items of the web site. Content items may include: text, image, audio and video information. | Globally identify content owners, secondary content providers and approvers for content on the site and clearly communicate and make available information.
eCommerce (Sales of/for training, events, other). Also, ICNet connected to web site | Provide eCommerce capabilities on the website that allow clients to purchase education classes, etc. Tie events, inquiries and client infomration, email opt ins into ICNet to measure success. | Determine what audiences can be served via eCommerce. Develop a list of products and services. Develop a behavior model for each audience. Find a way to tie ICNet into web site.
QA / Staging Site | Develop a staging area will be used to test changes to the website before the proposed change goes live. | Determine the capital and staffing requirments.
Integrated Marketing Development & Management | Standardize a global process for campaign development that includes: processes, roles/responsbilities and templates for expeditiously building, maintaining and retiring marketing programs. | Create flowcharts for campaign development that include owners, contributors, timeframes and examples of work. Develop specific reports to evaluate the ROI for each program.

## Setting Objectives
Setting Objectives
Objective | Business Strategy | Economic Impact
The redesigned home page must drive through new clients to seek services provided and promoted. | • Support the revenue streams driven by / through headquarters special services. • Support the maintenance or the increase of funding through other sources (govt, stakeholders). • Efficiently handle upsell and cross selling opportunities. | • Financing • Revenue • Visitors • Conversion • Clients • Trainees
The redesigned home page must provide a user experience that supports the brand promise while stimulating a measureable response. | • Increase brand loyalty. • Increase referals selling. • Build a contact funnel. | • Financing • Revenue • Visitors • Conversion • Clients • Trainees
The redesigned home page must incorporate drivers for all target markets to become more aware of services and successes to ultimately inspire emotional loyalty. | • To reach new entrepreneurs as well as owners of existing (long term) business, multiple tactics will be applied to draw upon including content, language, keywords. | • Financing • Revenue • Visitors • Conversion • Clients • Trainees

## Behavior Model
Behavior Model
1 | Trigger | How did the concept come up?
Compelling event
Word of Mouth
Prior relationship
Program
Ad/PR
2 | Consider | How would you even consider?
ROI
Price
Budget
Key objectives
Market adaptation
Competitiveness
Existing vendor relationship
3 | Search | What would you look for?
Ease of use
Functionality
Analyst reports
Perceived value
Success stories
Domain expertise
Customer support
Total cost of employment
4 | Choose | What is the basis for our selection?
Cost
Risk
Vision
Technology
Relationship
Financial viability
Prior expereinces
Customer support
5 | Buy | Whats the buying process?
SOW
Contracts
Signatures
Negotiation
Procurement
6 | Experience | What is important from the experience?
Customer support
Training & education
Implementation / planning
Ongoing account management
Direct communications

## Details-Review
Additional details of the May 2016 Home Page that should be considered
· Vertical Menu @ Slider (Automate, as much as possible)
o What’s New: Automate via RSS feeds to incorporate NJSBDC news around the web
o Articles: Currently lists links to the Newsletter.
§ Possibly change to social media feed.
o Blog: Continue to keep blogs linked to homepage feed.
· Request for Consulting / SBDC Center Near You
o Redundant.
o Needs rewording but significant and positioned properly.
· Special Events/ Training
o Special Events:
§ Needs to automate via RSS feed.
§ Must find method to incorporate event date as primary significance, as opposed to publish date.
§ Shy to identify 3 key items that need to be in Special Event space.
o Training already automated via RSS feed.
· Go Green
o Not noting importance to small business community
o Banner may be listed as condition of grant for static visibility on homepage. May be moved to an item on the top horizontal menu, with additional visibility in the slider. ?? Must confirm, but should remove if unnecessary.
· Growing Your Business/ Starting Your Business/ Doing Business in New Jersey
o Imaging should be synonymous with Big Impact concept/ design
· Sponsors/ Partners
o Sponsor/ partner visibility via homepage is needed. Consider changing layout